SeekEatz

Pre-Launch Content Playbook

March 6 – 26, 2026  |  20 Days to Launch

Instagram  •  TikTok  •  Reddit  •  Email

Ready-to-post captions, hooks, scripts, and a day-by-day calendar

# 01  |  Strategy Brief

🎯  You have 20 days. Every post needs to do one thing: drive people to your waitlist link. Secondary goal: build a community of health-conscious food lovers who feel like they discovered something before everyone else.

## The 3-Phase Framework

| Phase | Dates | Goal |
| --- | --- | --- |
| Phase 1: Tease | Mar 6–12 | Build curiosity. Don't reveal everything. Get follows + waitlist signups. |
| Phase 2: Educate | Mar 13–20 | Show the problem you solve. Demo the product. Build FOMO. |
| Phase 3: Launch Push | Mar 21–26 | Urgency. Social proof. Final waitlist push. Countdown. |

## Platform Strategy

Instagram: Your primary brand-building channel. Use Reels to reach new audiences, Stories to drive direct waitlist clicks with link stickers, and feed posts to anchor your aesthetic.

TikTok: Your highest-leverage awareness driver. One viral video can generate thousands of signups. Lean into food content, "what I eat" trends, and honest storytelling.

Reddit: The most underrated channel for this product. Fitness, nutrition, and foodie subreddits are full of your exact user. Post genuinely helpful content — no spam.

Email: Your most direct line to people already interested. Send 3 emails before launch: welcome, product preview, and launch-day countdown.

## Non-Negotiable Rules

- Every caption ends with a CTA to your waitlist link (put it in bio / link in bio)

- Post at minimum: 1x per day on Instagram Stories, 3-4x per week on Feed/Reels, 3-4x per week on TikTok

- Respond to every comment within 2 hours for the first 48 hours after posting

- Never launch a post without hashtags (see hashtag strategy at end)

- Screenshot every signup milestone and share it as a Story

# 02  |  20-Day Content Calendar

This calendar shows WHAT to post each day and WHERE. Detailed copy for each post follows in the channel sections.

PHASE 1: TEASE (MAR 6–12) — BUILD CURIOSITY, GET FOLLOWERS & WAITLIST SIGNUPS

| Day | Date | Instagram | TikTok | Reddit / Email |
| --- | --- | --- | --- | --- |
| 1 | Mar 6 (Fri) | Feed: 'I built something for people tired of tracking calories' — teaser image | Video: 'POV: you want to eat out without ruining your goals' — hook video | — |
| 2 | Mar 7 (Sat) | Story: Poll — 'How do you track meals when eating out?' Yes/No | Video: 'Things that are hard about eating healthy at restaurants' — relatable list | — |
| 3 | Mar 8 (Sun) | Reel: 'The problem with calorie tracking apps (and what we built instead)' | — | Reddit Post #1: r/loseit |
| 4 | Mar 9 (Mon) | Story: 'We're building something that changes how you find food' + waitlist link | Video: 'This is what SeekEatz does' — 60-sec product tease | Email #1: Welcome / waitlist confirmation |
| 5 | Mar 10 (Tue) | Feed: Aesthetic meal card mockup — 'This is what finding food should look like' | Video: 'Why I stopped using MyFitnessPal for restaurant meals' | — |
| 6 | Mar 11 (Wed) | Story: 'X people on the waitlist — are you one of them?' countdown | — | Reddit Post #2: r/MacroFactor |
| 7 | Mar 12 (Thu) | Reel: 'Week 1 of building SeekEatz' — founder POV, build in public | Video: 'This is what the app looks like (sneak peek)' | — |

PHASE 2: EDUCATE (MAR 13–20) — SHOW THE PROBLEM YOU SOLVE, BUILD FOMO

| Day | Date | Instagram | TikTok | Reddit / Email |
| --- | --- | --- | --- | --- |
| 8 | Mar 13 (Fri) | Feed: 'We analyze restaurant menus so you don't have to' — product feature post | Video: 'What 500 calorie meals actually look like at [popular chain]' | — |
| 9 | Mar 14 (Sat) | Story: 'What's your biggest struggle eating healthy?' Q&A box | Video: 'I found every high-protein meal at Chipotle under 600 cals' | Reddit Post #3: r/Fitness |
| 10 | Mar 15 (Sun) | Reel: Product walkthrough — onboarding flow + meal card demo | Video: 'SeekEatz vs. manually tracking — watch this' | — |
| 11 | Mar 16 (Mon) | Feed: 'AI-suggested swaps' feature — show a real before/after swap | Video: 'I tried to find a 600 calorie dinner at 5 different restaurants' | Email #2: Product preview |
| 12 | Mar 17 (Tue) | Story: Beta user quotes (even from friends) — 'Here's what people are saying' | — | Reddit Post #4: r/CICO |
| 13 | Mar 18 (Wed) | Reel: 'The problem we set out to solve' — founder story, 30-second version | Video: 'Why it's impossible to eat healthy at restaurants (data)' | — |
| 14 | Mar 19 (Thu) | Feed: Waitlist milestone post — 'X people signed up — here's why' | Video: 'Full demo of SeekEatz — launch is in 1 week' | — |
| 15 | Mar 20 (Fri) | Story: '6 days to launch — last chance for early access' with link sticker | Video: '6 days until SeekEatz launches — here's the hype reel' | — |

PHASE 3: LAUNCH PUSH (MAR 21–26) — URGENCY, COUNTDOWN, CONVERSION

| Day | Date | Instagram | TikTok | Reddit / Email |
| --- | --- | --- | --- | --- |
| 16 | Mar 21 (Sat) | Feed: '5 days countdown' — biggest problem SeekEatz solves | Video: '5 days. Here's everything SeekEatz does' | — |
| 17 | Mar 22 (Sun) | Story: 'Tag a friend who needs this' — shareable feature graphic | Video: 'The story of why I built SeekEatz' — personal, emotional hook | — |
| 18 | Mar 23 (Mon) | Reel: '3 days — you're going to want early access for this' | Video: 'POV: You find the perfect meal in 30 seconds' | Email #3: Launch countdown — 3 days |
| 19 | Mar 24 (Tue) | Feed: '2 days — every early user gets [benefit]' | Video: 'I tried every food tracking app so you don't have to' | Reddit Post #5: r/EatCheapAndHealthy |
| 20 | Mar 25 (Wed) | Story: 'Tomorrow is the day. Are you on the list?' + urgency CTA | Video: 'TOMORROW WE LAUNCH — last chance for early access' | — |
| 21 | Mar 26 (Thu) | Reel: LAUNCH DAY — 'SeekEatz is LIVE. Here's how to use it.' | Video: 'WE ARE LIVE — SeekEatz just launched' | Email: LAUNCH — We're live! |

# 03  |  Instagram — Ready-to-Post Content

Copy each caption exactly as written. Replace [WAITLIST LINK] with your actual URL. Tailor emoji use to your brand voice if needed.

## Feed Posts

### Post 1 — Day 1 Teaser (Mar 6)

Instagram — Feed Post — Photo or Graphic Finding healthy food when you're eating out is broken. You open a menu. Nothing has macros. You guess. You log it. It's wrong. You give up. We built SeekEatz so you never have to do that again. AI-powered meal discovery. Real restaurant food. Matched to YOUR calorie and macro goals — without the manual tracking. We launch March 26. Waitlist is open now. 👇 Link in bio. #SeekEatz #HealthyEating #MacroTracking #FoodTech #NutritionApp #HealthyFood #FitnessTech #CleanEating #MealPlanning #CalorieCounting 📌 Use a clean, minimal graphic with the SeekEatz logo or an aesthetic food photo. Keep it simple and striking.

### Post 2 — Meal Card Mockup (Mar 10)

Instagram — Feed Post — Product Mockup This is what finding healthy food should feel like. Real meals. Real restaurants. Real macros. Matched to your goals in seconds. No spreadsheets. No guessing. No guilt. SeekEatz is almost here. ↗️ Waitlist is open — link in bio. 📅 Launch: March 26 #SeekEatz #HealthyEating #NutritionApp #FoodApp #MacroFriendly #HealthTech #FitnessFood #EatSmart #CalorieTracker #FoodDiscovery 📌 Show a polished meal card UI mockup. This is your most shareable visual — invest time in making it look premium.

### Post 3 — AI Swaps Feature (Mar 16)

Instagram — Feed Post — Feature Highlight You ordered a burger. Your AI said: 'Try this instead — 200 fewer calories, same macros.' That's SeekEatz. Our AI-powered swap engine doesn't tell you what NOT to eat. It tells you what to eat INSTEAD — so you stay on track without skipping the things you love. 🔄 SeekEatz suggests smarter swaps in real time. 📊 Estimated macros on every meal card. 🎯 Matched to YOUR daily goals. Launching March 26. Get early access 👇 Link in bio. #SeekEatz #AIFood #SmartEating #MacroSwap #HealthySwaps #FoodAI #NutritionTech #EatSmart #HealthyAlternatives #FoodHacks 📌 Create a before/after visual: a standard meal on the left, the AI-suggested swap on the right with macro comparison.

### Post 4 — Waitlist Milestone (Mar 19)

Instagram — Feed Post — Social Proof [X] people already on the waitlist. Here's what they told us: 'I've been waiting for something like this.' 'This is the app I've been trying to build in my head for years.' 'Finally — something that works for how I actually eat.' We launch in 1 week. If you're not on the list, you're missing early access. 👇 Link in bio. #SeekEatz #ProductLaunch #AppLaunch #FoodTech #HealthyEating #WaitlistOpen #EarlyAccess #NutritionApp #FitnessApp #HealthTech 📌 Replace [X] with your actual waitlist count. If you don't have real quotes, use paraphrased feedback from beta users or friends who tested it.

## Reels — Video Concepts + Scripts

### Reel 1 — 'The Problem' (Mar 8)

Instagram — Reel — 30-45 seconds HOOK (on screen text + voice): 'Why is it so hard to eat healthy when you're eating out?' [Cut to: screenshot of a restaurant menu with no nutrition info] Voice: 'No calories. No macros. Just vibes.' [Cut to: MyFitnessPal search showing 47 different versions of 'chicken sandwich'] Voice: 'And if you try to track it, this happens.' [Cut to: person closing their phone in frustration] Voice: 'So most people give up. Every single day.' [Cut to: SeekEatz meal card appearing] Voice: 'We built SeekEatz to fix this. AI-powered meal discovery, matched to your exact goals. Launching March 26.' CTA on screen: 'Join the waitlist. Link in bio.' --- CAPTION: Struggling to find healthy food when you eat out? You're not alone. SeekEatz fixes this. Link in bio 👆 #SeekEatz #HealthyEating #CalorieTracking #FoodTech #NutritionTips 📌 Film this with screen recordings + face cam or voice-over style. Keep energy high. This is your top-of-funnel Reel.

### Reel 2 — Product Walkthrough (Mar 15)

Instagram — Reel — 45-60 seconds (screen recording) HOOK: 'Watch me find a 600-calorie dinner in 30 seconds' [Screen recording: Open SeekEatz — enter goal: 600 cal, high protein] Voice: 'I set my goal — 600 calories, 40g protein' [Meal cards appear filtered to goal] Voice: 'SeekEatz pulls real restaurant meals that actually match.' [Click a meal card — macros appear] Voice: 'Full estimated macros on every card.' [AI swap pops up: 'Try this — 90 fewer calories, same protein'] Voice: 'And if something's close but not perfect — the AI suggests a smarter swap.' [Final screen: full meal selected] Voice: 'Done. Dinner decided. No tracking. No guessing.' CTA: 'Launching March 26. Early access link in bio.' --- CAPTION: 30 seconds to find your perfect meal. This is SeekEatz — launching March 26. 🔗 Link in bio. #SeekEatz #AppDemo #HealthyEating #FoodApp #MacroTracking #FoodTech 📌 This is your most important Instagram video. Polish the screen recording — use a clean demo environment, no notifications showing.

### Reel 3 — Founder Story (Mar 18)

Instagram — Reel — 30-45 seconds (talking head) HOOK: 'I built SeekEatz because I was sick of lying to myself about what I ate.' 'Every time I ate out, I'd either skip tracking entirely — or spend 10 minutes guessing in MyFitnessPal and still be wrong.' 'I wanted to eat at real restaurants, without destroying my goals. And I couldn't find an app that helped.' 'So I built one.' 'SeekEatz matches real restaurant and grocery meals to your exact calorie and macro goals. No manual tracking. No guessing.' 'We launch March 26. If you've ever felt like I did, the waitlist link is in my bio.' --- CAPTION: I built SeekEatz because I needed it. Launching March 26. 🔗 Link in bio. #SeekEatz #FounderStory #BuildInPublic #FoodTech #HealthyEating #StartupLife 📌 Film this authentically — conversational, face-to-camera. Don't over-produce it. The rawness is the point.

# 04  |  TikTok — Video Scripts

TikTok is your highest-volume, highest-reach channel. Post 4-5x per week minimum. Mix product content with food/fitness content that provides standalone value — this builds the audience that converts to users.

## TikTok Video Scripts

### Video 1 — Hook Video (Mar 6)

TikTok — 60 seconds — talking head or POV HOOK (first 3 seconds): 'POV: You want to eat out but you're on a 1,800 calorie goal' [Scene: someone staring at a menu, overwhelmed] Text on screen: 'The struggle is real.' 'Here's the problem — restaurant menus don't tell you how many calories are in anything. So you either guess, skip eating out entirely, or say forget it and blow your goals.' 'Every. Single. Week.' 'We built SeekEatz to fix this. You enter your calorie and macro goals, tell us your diet and allergies, and we show you real restaurant meals that actually match.' 'No tracking. No guessing. No guilt.' 'We launch March 26. Link in bio to get early access.' --- CAPTION: The meal tracking struggle is REAL. SeekEatz fixes it. Launching 3/26 🔗 bio #SeekEatz #HealthyEating #CalorieTips #FoodTikTok #NutritionTips #HealthyFood #FitTok #MealPrep #FoodHacks #EatingHealthy 📌 Hook in first 3 seconds is CRITICAL. Test different hooks. Film 2-3 versions with different opening lines.

### Video 2 — Relatable Pain Point (Mar 7)

TikTok — 30-45 seconds — list format / trending sound HOOK: 'Things that are impossible when you're trying to eat healthy' [Text pops up with each point, trending sound in background] #1: Finding a meal at a restaurant under your calorie goal #2: Figuring out the macros when there's no nutrition info #3: Trusting the estimates in MyFitnessPal #4: Not ordering fries because you 'have no idea what's in them' #5: Eating out with friends and not spiraling [Cut to SeekEatz logo] 'We built something for this. Link in bio.' --- CAPTION: Eating healthy when you eat out is unnecessarily hard. We're fixing it. 🔗 bio #HealthyEating #CalorieCounting #MacroTracking #FitTok #NutritionTips #FoodTikTok #EatingOut #HealthyFood 📌 Use a trending sound from the 'relatable list' format. This style gets massive saves and shares.

### Video 3 — App Demo (Mar 9)

TikTok — 60 seconds — screen recording + voice HOOK: 'I'm gonna find a 500-calorie dinner at a real restaurant in under 60 seconds. Watch.' [Open SeekEatz — show home screen] 'Okay. 500 calories, 40g protein. Let's go.' [Filter — meals appear] 'Already filtered — showing me real options from actual restaurants near me.' [Click first card] 'Grilled chicken bowl — 490 cals, 42g protein, 8g fat. That's actually perfect.' [AI swap appears] 'And look — the AI flagged a swap. Dressing on the side saves 70 calories. Done.' 'That took 40 seconds. No MyFitnessPal. No guessing. No stress.' 'SeekEatz. Launching March 26. Link in bio for early access.' --- CAPTION: 40 seconds to find the perfect meal. SeekEatz launches 3/26 🔗 bio #SeekEatz #AppDemo #FoodApp #HealthyEating #MacroTracking #FoodTech #FitTok #NutritionApp 📌 Show real UI. Use voiceover with energy. The speed and ease is your strongest selling point — demonstrate it visually.

### Video 4 — Restaurant Hack Format (Mar 14)

TikTok — 45-60 seconds — food content hybrid HOOK: 'High protein meals under 600 calories at Chipotle (that actually taste good)' [Show Chipotle menu / walk through options] 'Number one: Chicken Bowl — white rice, beans, chicken, salsa, no cheese or sour cream. About 570 cals, 40g protein.' 'Number two: Barbacoa Bowl — same build, 560 cals, 38g protein. Lower fat.' 'Number three: Burrito Bowl, protein swap to half chicken half sofritas — 520 cals, 35g protein.' [Cut to phone showing SeekEatz] 'This is exactly what SeekEatz does — but for thousands of restaurants, automatically, matched to YOUR exact goal.' 'No research required. Just open the app.' 'Launching March 26. Link in bio.' --- CAPTION: Chipotle macros 🌯 + the app that finds this for you automatically. Launching 3/26 🔗 #Chipotle #HighProtein #MacroFriendly #HealthyFast #FitTok #FoodHacks #NutritionTips #SeekEatz #EatingHealthy 📌 This hybrid format (food tips + product) is the most effective TikTok strategy for this product. Do this for multiple chains: Chick-fil-A, Panera, McDonald's, Starbucks.

### Video 5 — Founder Story (Mar 22)

TikTok — 60-90 seconds — emotional, face-to-camera HOOK: 'I spent $40,000 and 2 years building an app because I was tired of lying to myself about food.' 'Here's the honest truth. I've tried every calorie tracking app. I've logged meals. I've given up. Started over. Given up again.' 'The problem was never willpower. The problem was that these apps are built for people who cook at home. Not people who eat out three, four, five times a week.' 'Restaurant food? You're guessing. Every single time.' 'I built SeekEatz because I wanted to eat out without destroying my goals — and there was nothing that actually helped.' 'We match real restaurant and grocery meals to your exact calorie and macro goals. AI swaps. No tracking. Just — here's what you can eat.' 'We launch March 26. I built this for people who've given up on tracking. I hope it changes things for you the way it changed them for me.' 'Link in bio. Come join us.' --- CAPTION: I built SeekEatz for people who've given up on calorie tracking. We launch March 26. 🔗 bio #FounderStory #SeekEatz #FoodTech #BuildInPublic #HealthyEating #StartupTikTok #AppLaunch 📌 This is your most emotionally resonant video. It will earn follows, saves, and shares. Be genuine — this isn't a pitch, it's a story. Film it in one take if possible.

# 05  |  Reddit — Posts & Strategy

⚠️  Reddit requires a different approach. Never post a direct ad. Post genuinely helpful content that happens to mention SeekEatz. Be a user, not a marketer. Engage in comments for hours after posting.

## Target Subreddits

| Subreddit | Why It Works | Post Approach |
| --- | --- | --- |
| r/loseit | Active calorie deficit community — exact pain point | Post about the struggle of tracking restaurant meals |
| r/MacroFactor | Power users of macro tracking — sophisticated audience | Tech-forward angle: 'AI meal matching for restaurant food' |
| r/Fitness | Huge audience, nutrition questions are common | Post as a resource, not a promotion |
| r/CICO | Calorie In Calorie Out — direct product-problem fit | 'I built a solution to [specific CICO pain point]' |
| r/EatCheapAndHealthy | Large, active, food-focused audience | Post the best low-cal restaurant options by chain |
| r/mealprep | People who care deeply about nutrition | 'For when meal prep fails — how to stay on track eating out' |

## Reddit Post Templates

### Reddit Post 1 — r/loseit (Mar 8)

Reddit — Discussion Post Title: Does anyone else feel like tracking restaurant meals is basically impossible? Body: I've been doing CICO for about a year now and I'm pretty consistent when I cook at home. But the moment I eat out, I feel like I'm just making up numbers. I'll search for 'chicken sandwich' in MyFitnessPal and get 47 different entries ranging from 380 to 890 calories. Then I pick one in the middle and hope for the best. Honestly it's made me avoid eating out altogether which is... not sustainable. I want to be able to live a normal social life and still hit my goals. Has anyone found a good system for this? I've tried looking up chain restaurant nutrition PDFs but it doesn't work for local spots. [After a few comments, or if someone asks: 'I actually got so frustrated with this that I started building an app for it — it's called SeekEatz and it uses AI to match real restaurant meals to your calorie/macro goals. Just launched a waitlist at seekeatz.com if anyone wants to check it out — I'd love honest feedback from people who actually deal with this problem.'] 📌 Post the body first WITHOUT mentioning SeekEatz. Let it get traction. Add the product mention naturally in a comment reply when it's organic. This avoids the spam filter and builds credibility.

### Reddit Post 2 — r/Fitness (Mar 9)

Reddit — Resource / Guide Post Title: Complete macro breakdown for the most popular fast casual chains (Chipotle, Sweetgreen, Panera, Chick-fil-A) Body: [Include actual macro data for 3-4 meals at each chain] I put this together because I got tired of hunting for accurate nutrition info. Most chain websites bury this stuff. Chipotle — Best options under 600 cal: • Chicken Bowl (no cheese/sour cream): ~570 cal, 40g protein • Sofritas Bowl (vegan): ~520 cal, 22g protein ... [Continue with other chains] Happy to add more chains if people find this useful. I'm actually building a tool that automates this for any restaurant — DM me or check the comments if you want to know more when it launches. 📌 This is a value-first post. The SeekEatz mention should feel like a natural epilogue. This type of post gets saved/bookmarked constantly and drives sustained traffic.

### Reddit Post 3 — r/CICO (Mar 12)

Reddit — Show HN / Founder Post Title: I built an app because tracking restaurant meals was destroying my CICO consistency — feedback welcome Body: Background: I've been doing CICO for 2+ years. Great at home. Completely failed every time I ate out. Tracked 47 variations of 'pasta' in MyFitnessPal and still felt like I was guessing. So I built SeekEatz — it's an AI-powered meal discovery app that lets you enter your calorie and macro goals and see real restaurant and grocery meals that match. Estimated macros on each card, AI-suggested swaps, filters for diet and allergies. We just opened a waitlist at seekeatz.com ahead of our March 26 launch. Honest question for this community: what would make you actually trust a tool like this? What's the #1 thing that breaks your confidence in restaurant calorie data? I'm here to answer questions and genuinely want feedback from people who take CICO seriously. 📌 This is a 'founder post' which CICO and similar communities often welcome when genuine. Be present in the comments for the full day after posting. Answer every question.

# 06  |  Email Sequences

You need 3 emails before launch. Short, direct, and personal. Don't write marketing copy — write like a founder talking to early believers.

## Email 1 — Welcome (Send Mar 9)

Instagram — Email Subject: You're in. Here's what SeekEatz actually is. Hi [First Name], You just joined the SeekEatz waitlist — and I wanted to write you personally. Here's the honest pitch: Finding healthy food when you eat out is broken. Restaurant menus don't show macros. Tracking apps are full of garbage data. Most people just give up. SeekEatz is an AI-powered meal discovery app. You enter your calorie and macro goals, set your diet preferences and allergies, and we show you real restaurant and grocery meals that actually match — with estimated macros on every card and AI-suggested swaps when something's close but not perfect. No manual tracking. No guessing. Just: here's what you can eat. We launch March 26. I'll send you one more email before launch — a preview of what the app looks like. If you have any questions or feedback, reply directly to this email. I read everything. — Isaac Founder, SeekEatz 📌 Replace with your actual name. Use a personal email sender (isaac@seekeatz.com, not noreply@). Short is better. No images needed.

## Email 2 — Product Preview (Send Mar 16)

Instagram — Email Subject: Here's what SeekEatz looks like (10 days to launch) Hi [First Name], 10 days until launch. I wanted to show you what we built. [Insert 1-2 product screenshots here — meal card view and onboarding] Here's how it works: 1. You tell us your daily calorie and macro goals 2. Set your diet (keto, vegan, paleo, etc.) and any allergies 3. Search by restaurant, cuisine, or macro target 4. Get matched meal cards — estimated macros on every one 5. If a meal is close but not perfect, our AI suggests a smarter swap That's it. No spreadsheets. No manual entry. No guessing. We launch March 26. You'll get an email that day with access. One thing: if you know someone who eats out a lot and tries to stay on track — forward this email. Word of mouth from people who get it is the best thing you can do for us right now. See you on the 26th. — Isaac 📌 This email should have 1-2 screenshots of the actual app. If the UI isn't polished enough, use a mockup. The product visual is critical for this email.

## Email 3 — Launch Day (Send Mar 26, 8am)

Instagram — Email Subject: SeekEatz is live. Here's your access. Hi [First Name], Today's the day. SeekEatz is officially live at [APP URL / APP STORE LINK]. You're one of the first people in. That matters to me — you joined before there was anything to see, and I don't take that lightly. Here's what to do right now: 1. Download / open SeekEatz at [LINK] 2. Complete the 2-minute onboarding (set your goals, diet, allergies) 3. Find your first meal — takes less than 60 seconds After you try it: please reply to this email and tell me what you think. What worked, what didn't, what you wish it did. I will personally read every response. If you love it: share it. Post about it. Send the link to a friend who eats out and tries to stay healthy. Your word of mouth is the only marketing that matters right now. Thank you for believing in this before it existed. Let's go. — Isaac Founder, SeekEatz P.S. If something doesn't work, email me directly. We're a small team and we'll fix it fast. 📌 Send this at 8-9am on launch day. Make sure the link works BEFORE sending. Have someone test the full signup flow on mobile the night before.

# 07  |  Hashtag Strategy

Use different hashtag sets to avoid shadowbanning. Rotate between 3-4 sets per platform. Mix high-volume and niche tags.

## Instagram Hashtag Sets

### Set A — Health & Nutrition Focus

#SeekEatz #HealthyEating #MacroTracking #CalorieTracking #NutritionApp #CleanEating #HealthyFood #FoodTech #FitnessFood #EatSmart #MacroFriendly #FoodDiscovery #HealthTech #NutritionTips #HealthyMeals

### Set B — Fitness Community Focus

#SeekEatz #FitFood #FitFam #GymFood #BodyRecomp #HighProtein #MealPrep #FitnessGoals #CalorieCounting #MacroFit #FoodTracking #HealthyLifestyle #FitnessTips #NutritionCoach #EatWell

### Set C — Food Discovery Focus

#SeekEatz #FoodApp #AppLaunch #FoodDiscovery #RestaurantFood #EatOut #FoodLovers #FoodieApp #TechFood #FoodInnovation #SmartEating #FoodAI #MealFinder #HealthyRestaurant #WhatToEat

### Set D — Broad Reach

#SeekEatz #HealthyEating #FoodTech #MealPlanning #CalorieCount #MacroCount #FoodLife #EatingHealthy #NutritionGoals #FoodLover #HealthyChoices #StartupLife #AppLaunch #ProductLaunch #Wellness

## TikTok Hashtag Sets

### Primary TikTok Set

#SeekEatz #FoodTikTok #HealthyEating #CalorieTips #FitTok #NutritionTips #FoodHacks #HealthyFood #EatingHealthy #MacroTracking #FoodApp #AppLaunch #HealthTech #FoodTech

### Restaurant-Specific (for chain hack videos)

#[RestaurantName] #HealthyFastFood #MacroFriendly #HighProtein #LowCalorie #HealthyChoices #FoodHacks #NutritionFacts #SeekEatz #FitTok

# 08  |  Quick Wins (Do These This Week)

⚡  These 5 actions will generate more waitlist signups than any piece of content. Do them before you start posting.

| # | Action | Why It Matters |
| --- | --- | --- |
| 1 | Text 20 people personally — not a group text, individual messages: 'Hey, I launched a waitlist for SeekEatz — [link] — would mean a lot if you signed up and shared it' | Personal outreach converts 5-10x better than public posts. Your first 50 signups should come from people you know. |
| 2 | Pin your waitlist link to your Instagram bio with a clear CTA: 'Free early access — grab yours 👇' and add a link sticker to every single Story | Most people never click bio links. A link sticker in Stories converts at 5-8%. Do this every day. |
| 3 | Post a personal, vulnerable caption on Instagram today — not a product post, but a story about why you built this: 'I was tired of...' style | Founder story content outperforms product content in early-stage. People follow people, not apps. |
| 4 | DM every person who comments on your first TikTok with: 'Thanks for watching! We launch March 26 — link in my bio to grab early access' | DM conversion from engaged commenters is very high. This is manual but worth it for your first 100 signups. |
| 5 | Post in 1 relevant Facebook Group (fitness, healthy eating, local food scene) — genuine, helpful post + soft mention of SeekEatz | Facebook Groups are underrated for early-stage products. Healthy eating groups have millions of members and high engagement. |

## One Metric That Matters Before March 26

📊  DAILY WAITLIST SIGNUPS. That's it. Not followers, not likes, not views. Every single morning, check how many people signed up the day before. If it's not growing, change what you're doing — today.

Good luck. You have everything you need.

Now go post.